## Sheet1
Task Mode | ID | Task Name | Activity Id | Activity Name | Actor | Duration | Start | Finish | Predecessors | Successors
Manually Scheduled | 1 | MWCP2.0 | GL to start migration | Green light to start the migration |  | 0 mins | Mon 04/11/24 08:00 | Mon 04/11/24 08:00 |  | 31
Auto Scheduled | 2 |  | MWCP2.0 | ECB gives the green-light to start the Migration Weekend Preparation Weeks | ECMS Coordination Desk | 0 days | Mon 04/11/24 08:00 | Mon 04/11/24 08:00
Auto Scheduled | 3 | Operational Day | Business Day Change during test 3 | ECMS Operational Day Management |  | 16545 mins | Mon 04/11/24 07:00 | Fri 15/11/24 18:45
Manually Scheduled | 4 |  |  | Business day - 04/11/2024 |  | 705 mins | Mon 04/11/24 07:00 | Mon 04/11/24 18:45 |  | 5
Auto Scheduled | 5 |  | ECMS.OPD.SOD | Change of business date 05/11 | ECMS operator | 0 mins | Mon 04/11/24 18:45 | Mon 04/11/24 18:45 | 4 | 6
Auto Scheduled | 6 |  |  | Business day - 05/11/2024 |  | 24 hrs | Mon 04/11/24 18:45 | Tue 05/11/24 18:45 | 5 | 7
Auto Scheduled | 7 |  | ECMS.OPD.SOD | Change of business date 06/11 | ECMS operator | 0 mins | Tue 05/11/24 18:45 | Tue 05/11/24 18:45 | 6 | 8
Auto Scheduled | 8 |  |  | Business day - 06/11/2024 |  | 24 hrs | Tue 05/11/24 18:45 | Wed 06/11/24 18:45 | 7 | 9
Auto Scheduled | 9 |  | ECMS.OPD.SOD | Change of business date 07/11 | ECMS operator | 0 mins | Wed 06/11/24 18:45 | Wed 06/11/24 18:45 | 8 | 10
Auto Scheduled | 10 |  |  | Business day - 07/11/2024 |  | 24 hrs | Wed 06/11/24 18:45 | Thu 07/11/24 18:45 | 9 | 11
Auto Scheduled | 11 |  | ECMS.OPD.SOD | Change of business date 08/11 | ECMS operator | 0 mins | Thu 07/11/24 18:45 | Thu 07/11/24 18:45 | 10 | 12
Auto Scheduled | 12 |  |  | Business day - 08/11/2024 |  | 24 hrs | Thu 07/11/24 18:45 | Fri 08/11/24 18:45 | 11 | 13
Auto Scheduled | 13 |  | ECMS.OPD.SOD | Change of business date 11/11 | ECMS operator | 0 mins | Fri 08/11/24 18:45 | Fri 08/11/24 18:45 | 12 | 14
Auto Scheduled | 14 |  |  | Business day - 11/11/2024 |  | 72 hrs | Fri 08/11/24 18:45 | Mon 11/11/24 18:45 | 13 | 15
Auto Scheduled | 15 |  | ECMS.OPD.SOD | Change of business date 12/11 | ECMS operator | 0 mins | Mon 11/11/24 18:45 | Mon 11/11/24 18:45 | 14 | 16
Auto Scheduled | 16 |  |  | Business day - 12/11/2024 |  | 24 hrs | Mon 11/11/24 18:45 | Tue 12/11/24 18:45 | 15 | 17
Auto Scheduled | 17 |  | ECMS.OPD.SOD | Change of business date 13/11 | ECMS operator | 0 mins | Tue 12/11/24 18:45 | Tue 12/11/24 18:45 | 16 | 18
Auto Scheduled | 18 |  |  | Business day - 13/11/2024 |  | 24 hrs | Tue 12/11/24 18:45 | Wed 13/11/24 18:45 | 17 | 19
Auto Scheduled | 19 |  | ECMS.OPD.SOD | Change of business date 14/11 | ECMS operator | 0 mins | Wed 13/11/24 18:45 | Wed 13/11/24 18:45 | 18 | 20
Auto Scheduled | 20 |  |  | Business day - 14/11/2024 |  | 24 hrs | Wed 13/11/24 18:45 | Thu 14/11/24 18:45 | 19 | 21
Auto Scheduled | 21 |  | ECMS.OPD.SOD | Change of business date 15/11 | ECMS operator | 0 mins | Thu 14/11/24 18:45 | Thu 14/11/24 18:45 | 20 | 22
Auto Scheduled | 22 |  |  | Business day - 15/11/2024 |  | 24 hrs | Thu 14/11/24 18:45 | Fri 15/11/24 18:45 | 21 | 227
Auto Scheduled | 23 | Preparation Weeks | Preparation Weeks | Migration Weekend Preparation Weeks |  | 16620 mins? | Mon 04/11/24 08:00 | Fri 15/11/24 21:00
Auto Scheduled | 24 | System Prep PW |  | Preparation of the environement for the Migration Prepration Weeks |  | 240 mins | Mon 04/11/24 08:00 | Mon 04/11/24 12:00 |  | 119
Auto Scheduled | 31 | Ref. Data Synchronisation |  | Synchronisation of Reference Data with External Data Providers |  | 16080 mins | Mon 04/11/24 14:00 | Fri 15/11/24 18:00 | 1
Auto Scheduled | 119 | DWH setup |  | DWH setup |  | 15600 mins | Mon 04/11/24 12:00 | Fri 15/11/24 08:00 | 24
Manually Scheduled | 133 | Credit Claims Ref. Data - 1st window |  | Migration of Credit Claims Reference Data - 1st window |  | 14640 mins | Tue 05/11/24 08:00 | Fri 15/11/24 12:00
Auto Scheduled | 144 |  | ECMS.MIG.DATA.CCRF.PID1 | Provision of the ECMS CC Id to the Counterparties | NCBs | 5760 mins | Mon 11/11/24 12:00 | Fri 15/11/24 12:00 | 142SS
Auto Scheduled | 145 | T2S and TPA Ref Data Preparation |  | Provision of reference data to T2S and TPA |  | 15060 mins | Tue 05/11/24 08:00 | Fri 15/11/24 19:00
Auto Scheduled | 182 | Undesirable intructions |  | Possible CTPY instruction restrictions and freezing period |  | 16560 mins? | Mon 04/11/24 08:00 | Fri 15/11/24 20:00
Auto Scheduled | 183 |  | outside ECMS | Apply Credit Claims Registration restrictions | NCBs | 15000 mins? | Mon 04/11/24 08:00 | Thu 14/11/24 18:00
Manually Scheduled | 185 |  | outside ECMS | Request CTPY to demobilise MA affected by CA event to be paid after the go-live | NCBs | 15000 mins? | Tue 05/11/24 08:00 | Fri 15/11/24 18:00
Manually Scheduled | 186 |  | outside ECMS | Apply instruction restrictions to elective CA event to be paid after the go-live | NCBs | 15000 mins? | Tue 05/11/24 08:00 | Fri 15/11/24 18:00
Manually Scheduled | 187 |  | outside ECMS | Reject collateral instructions with intended settlement date after go-live | NCBs | 15000 mins? | Tue 05/11/24 08:00 | Fri 15/11/24 18:00
Manually Scheduled | 188 |  | outside ECMS | Request CTPY to close pending settlement instructions | NCBs | 10 hrs | Fri 15/11/24 08:00 | Fri 15/11/24 18:00
Manually Scheduled | 189 |  | outside ECMS | Apply agreed cutoff for CCMB instructions | NCBs | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00
Manually Scheduled | 190 |  | outside ECMS | Cancel unmatched settlement instructions | NCBs | 360 mins | Fri 15/11/24 12:00 | Fri 15/11/24 18:00
Manually Scheduled | 191 |  | outside ECMS | Provide CCBM statements of holdings to HCB | NCBs | 2 hrs | Fri 15/11/24 18:00 | Fri 15/11/24 20:00
Auto Scheduled | 192 | MWCP2.1 | Completion of Migration WE Preparation Weeks | Completion of Migration Weekend Preparation Weeks Activities |  | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00 |  | 197
Auto Scheduled | 193 |  | MWCP2.1 | Confirmation of the synchronisation of data with external provider | ECMS operator | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00
Auto Scheduled | 194 |  | MWCP2.1 | Confirmation of DWH setup | NCB Migration Managers | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00
Auto Scheduled | 195 |  | MWCP2.1 | Confirmation of migration of credit claim reference data part 1 | NCB Migration Managers | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00
Auto Scheduled | 196 |  | MWCP2.1 | Confirmation of the provision of reference data to T2S and TPAs | NCB Migration Managers | 0 mins | Fri 15/11/24 12:00 | Fri 15/11/24 12:00
Auto Scheduled | 197 | System Prep. MW |  | Preparation of the environement - Migration Weekend |  | 180 mins | Fri 15/11/24 12:00 | Fri 15/11/24 15:00 | 192
Auto Scheduled | 204 | Closing of Local CMSs |  | NCB readiness to start migration activities / Business closure of local CMSs |  | 1560 mins? | Thu 14/11/24 19:00 | Fri 15/11/24 21:00 |  | 210
Manually Scheduled | 207 | MWCP2.2 | Start of Migration Wekend | Confirmation that the Migration Weekend activities can start |  | 0 mins | Fri 15/11/24 21:00 | Fri 15/11/24 21:00 |  | 213211
Auto Scheduled | 208 |  | MWCP2.2 | Confirmation of System prepration for the migration weekend | ECMS operator | 0 mins | Fri 15/11/24 21:00 | Fri 15/11/24 21:00
Auto Scheduled | 209 |  | MWCP2.2 | Confirmation of T2S,CLM,TOP switch to ECMS configuration request | ECB Migration Coordinator | 0 mins | Fri 15/11/24 21:00 | Fri 15/11/24 21:00
Auto Scheduled | 210 |  | MWCP2.2 | Confirmation of NCB readiness to start the migration weekend | NCB Migration Managers | 0 mins | Fri 15/11/24 21:00 | Fri 15/11/24 21:00 | 204
Auto Scheduled | 211 | Migration Weekend | Migration Weekend | Migration Weekend |  | 45540 mins | Fri 15/11/24 21:00 | Tue 17/12/24 12:00 | 207
Auto Scheduled | 212 | Credit Claims Ref. Data - 2nd window |  | Migration of Credit Claims Reference Data - 2nd window |  | 180 mins | Fri 15/11/24 21:00 | Sat 16/11/24 00:00 |  | 237
Auto Scheduled | 213 |  | ECMS.MIG.DATA.CCRF.MIG2 | Last Updates of Credit Claim Reference Data | NCBs | 3 hrs | Fri 15/11/24 21:00 | Sat 16/11/24 00:00 | 207 | 214SS
Auto Scheduled | 214 |  | ECMS.MIG.DATA.CCRF.REC2 | Reconciliation and repair of the Credit Claim Ref Data | NCBs | 3 hrs | Fri 15/11/24 21:00 | Sat 16/11/24 00:00 | 213SS | 215SS
Auto Scheduled | 215 |  | ECMS.MIG.DATA.CCRF.PID2 | Provision of the ECMS CC Id to the Counterparties | NCBs | 3 hrs | Fri 15/11/24 21:00 | Sat 16/11/24 00:00 | 214SS
Auto Scheduled | 216 | Transactional DDT files Preparation |  | Preparation and upload of DTT file for migration of transactional data |  | 600 mins | Fri 15/11/24 21:00 | Sat 16/11/24 07:00 |  | 238
Auto Scheduled | 226 | NTP Friday->Saturday |  | Weekend process to be executed prior to the migration |  | 600 mins | Fri 15/11/24 21:00 | Sat 16/11/24 07:00 |  | 239
Auto Scheduled | 227 |  | ECMS.OPD.SOD | Change of business date 18/11 | ECMS operator | 0 mins | Fri 15/11/24 21:00 | Fri 15/11/24 21:00 | 22 | 228229
Manually Scheduled | 236 | MWCP2.3 | Start of Migration of Transactional Data | Confirmation that the migration of transactional data can start |  | 0 mins | Sat 16/11/24 07:00 | Sat 16/11/24 07:00 |  | 254
Auto Scheduled | 237 |  | MWCP2.3 | Confirmation by NCB of the full migration of Credit Claims Ref data | NCB Migration Managers | 0 mins | Sat 16/11/24 07:00 | Sat 16/11/24 07:00 | 212
Auto Scheduled | 238 |  | MWCP2.3 | Confirmation by NCB of the upload of the DTT files | NCB Migration Managers | 0 mins | Sat 16/11/24 07:00 | Sat 16/11/24 07:00 | 216
Auto Scheduled | 239 |  | MWCP2.3 | Confirmation of the completion of expected NTP from Friday ot Saturday | ECMS operator | 0 mins | Sat 16/11/24 07:00 | Sat 16/11/24 07:00 | 226
Auto Scheduled | 240 | Migration of Collateral Positions |  | Migration of Collateral Positions |  | 300 mins | Sat 16/11/24 07:00 | Sat 16/11/24 12:00
Auto Scheduled | 253 | Migration of TPA Positions |  | Migration of Triparty Positions by TPA using colr messages |  | 480 mins | Sat 16/11/24 07:00 | Sat 16/11/24 15:00
Auto Scheduled | 257 | Sync. Point - Collat | ECMS.MIG.DATA.COLSYNC | Collateral Position Migration Synchronisation Point | NCB Migration Managers | 0 mins | Sat 16/11/24 12:00 | Sat 16/11/24 12:00 | 2.4224e+17 | 265258
Auto Scheduled | 258 | Migration of Credit Positions |  | Migration of Credit Positions |  | 240 mins | Sat 16/11/24 12:00 | Sat 16/11/24 16:00 | 257
Auto Scheduled | 263 | Sync. Point - Credit | ECMS.MIG.DATA.CRSYNC | Synchronisation of Credit Positions Migration | NCB Migration Managers | 0 mins | Sat 16/11/24 16:00 | Sat 16/11/24 16:00 | 260262 | 265
Auto Scheduled | 264 | MWCP2.4 | Credit and Collateral Positions Migrated | Confirmation of the migration of collateral and credit positions |  | 0 mins | Sat 16/11/24 16:00 | Sat 16/11/24 16:00 |  | 266
Auto Scheduled | 265 |  | MWCP2.4 | Migration managers confirm the successful completion of the migrated collateral and credit positions | ECMS Coordination Desk, NCB Migration Managers | 0 mins | Sat 16/11/24 16:00 | Sat 16/11/24 16:00 | 257263
Auto Scheduled | 266 | Pool Valuation |  | 1st Pool Valuation |  | 30 mins | Sat 16/11/24 16:00 | Sat 16/11/24 16:30 | 264 | 275
Auto Scheduled | 275 | Pool Value Check |  | Check pools credit and collateral values |  | 270 mins | Sat 16/11/24 16:30 | Sat 16/11/24 21:00 | 266 | 280
Manually Scheduled | 277 | Constraint - Swift release |  | SWIFT Nov 24 release deployment |  | 3 hrs | Sat 16/11/24 17:00 | Sat 16/11/24 20:00 |  | 278
Auto Scheduled | 279 | MWCP2.5 | Pool Valuated | Confirmation of the pool valuation processes |  | 0 mins | Sat 16/11/24 21:00 | Sat 16/11/24 21:00 |  | 281284
Auto Scheduled | 280 |  | MWCP2.4 | Confirmation of the pool valuation (1st NTP) | Migration Managers | 0 hrs | Sat 16/11/24 21:00 | Sat 16/11/24 21:00 | 275 | 282
Auto Scheduled | 281 | Sending of GLF Record Type A |  | Sending of GL files for accrued interest over the weekend |  | 60 mins | Sat 16/11/24 21:00 | Sat 16/11/24 22:00 | 279
Manually Scheduled | 283 | Synch. Point - CLM | Synch. Point - CLM | CLM readiness to receive flows from ECMS (date alignment) | T2, ECMS | 0 days | Sat 16/11/24 21:00 | Sat 16/11/24 21:00 |  | 285286287288
Auto Scheduled | 284 | Send MCL to CLM |  | Sending MCL and Payments to CLM |  | 30 mins | Sat 16/11/24 21:00 | Sat 16/11/24 21:30 | 279 | 290
Auto Scheduled | 289 | CLM Impact Check |  | Check the update of the CL in CLM |  | 60 mins | Sat 16/11/24 21:30 | Sat 16/11/24 22:30
Auto Scheduled | 291 | MWCP2.6 | CLM impacted | Confirmation of the CL update in CLM |  | 0 mins | Sat 16/11/24 22:30 | Sat 16/11/24 22:30
Auto Scheduled | 292 |  | MWCP2.6 | Migration managers confirm the CL updates in CLM | Migration Managers | 0 days | Sat 16/11/24 22:30 | Sat 16/11/24 22:30 | 290
Manually Scheduled | 293 | Swift Release - Sync Point |  | End of SWIFT Nov 24 release deployment |  | 0 mins | Sat 16/11/24 20:00 | Sat 16/11/24 20:00 |  | 296295
Auto Scheduled | 294 | CA Migration |  | Migration of ongoing CA events |  | 840 mins | Sat 16/11/24 20:00 | Sun 17/11/24 10:00 |  | 298304
Auto Scheduled | 298 | Start CA processing |  | Start CA event processing |  | 360 mins | Sun 17/11/24 10:00 | Sun 17/11/24 16:00 | 294
Auto Scheduled | 301 |  | ECMS.MW.CA.NOTIF1 | Sending of CANO/NEMW to the NCB participants (including CCB notifications to HCBs) | ECMS operator | 6 hrs | Sun 17/11/24 10:00 | Sun 17/11/24 16:00 | 300SS
Auto Scheduled | 304 | CA to be paid on the 18/11 |  | Processing of CA event to be paid on the 18/11 and creation of CA event leftovers |  | 360 mins | Sun 17/11/24 10:00 | Sun 17/11/24 16:00 | 294
Auto Scheduled | 309 | MWCP2.7 | Readyness to open ECMS to CPTY | End of Migration Activities - Greenlight to open the system to the counterparties |  | 0 mins | Sun 17/11/24 09:30 | Sun 17/11/24 09:30
Manually Scheduled | 310 |  | MWCP2.7 | Migration managers give the green light to open the system to the counterparties | Migration Managers | 0 days | Sun 17/11/24 09:30 | Sun 17/11/24 09:30 |  | 312
Auto Scheduled | 311 | Reactivation of CTPY users |  | Reactivation of the counterparty's users |  | 30 mins | Sun 17/11/24 09:30 | Sun 17/11/24 10:00 |  | 314317
Auto Scheduled | 312 |  | XX | Execute script to reactivate CTPY users access to the ECMS | ECMS operator | 30 mins | Sun 17/11/24 09:30 | Sun 17/11/24 10:00 | 310 | 313
Auto Scheduled | 313 |  | XX | Inform Counterparty they can access to the ECMS | NCBs | 0 mins | Sun 17/11/24 10:00 | Sun 17/11/24 10:00 | 312
Auto Scheduled | 314 | CTPY checks |  | Counterparties checks of the migrated positons |  | 360 mins | Sun 17/11/24 10:00 | Sun 17/11/24 16:00 | 311 | 322
Auto Scheduled | 315 |  | XX | Pool positions checks by the counterparties in U2A | Counterparties | 6 hrs | Sun 17/11/24 10:00 | Sun 17/11/24 16:00
Auto Scheduled | 316 |  | ECMS.MIG.POOL.REP | Generation of the pool positon reports upon reception of admin.005 | Counterparties | 6 hrs | Sun 17/11/24 10:00 | Sun 17/11/24 16:00
Auto Scheduled | 317 | Penny testing |  | Penny test post migration |  | 43320 mins | Sun 17/11/24 10:00 | Tue 17/12/24 12:00 | 311 | 322
Auto Scheduled | 318 |  | XX | Sample MA mobilisation instructions as part of the penny test | Selected CTPYs | 2 hrs | Sun 17/11/24 10:00 | Sun 17/11/24 12:00
Manually Scheduled | 320 | Constraint - T2/T2S Maintenance |  | Start of T2 and T2S Maintenance window |  | 0 hrs | Sun 17/11/24 10:00 | Sun 17/11/24 12:00
Auto Scheduled | 321 | MWCP2.8 | End of Migration Weekend | End of Migration Weekend Activities |  | 0 mins | Tue 17/11/24 12:00 | Tue 17/11/24 12:00
Auto Scheduled | 322 |  | MWCP2.8 | Migration managers confirm successful completion of the migration weekend activities | NCB Migration Managers | 0 mins | Sun 17/11/24 10:00 | Sun 17/11/24 12:00 | 314317
Auto Scheduled | 323 | Start of Operations |  | Start of Operation Post Migration |  | 0 mins | Mon 18/11/24 07:00 | Mon 18/11/24 07:00
Manually Scheduled | 324 |  |  | Activation of daytime process | ECMS operator | 0 mins | Mon 18/11/24 07:00 | Mon 18/11/24 07:00 |  | 325
Auto Scheduled | 325 |  |  | Handover of the ECMS to Operational Manager | ECMS Coordination Desk | 0 mins | Mon 18/11/24 07:00 | Mon 18/11/24 07:00 | 324