## Sheet1
ID | Task Name | Activity Id | Activity Name | Actor | Duration | Start | Finish | Predecessors | Successors
| Registration Forms Submission |  | Registration Forms Submission
|  | ECMS.PM.CTPY.RF | CTPY Migration Registration Forms submission | Counterparty | Deadline defined at national level by the NCB, for its CTPYs, CSDs and TPAs
1 | PMCP0 |  | PMCP0 - Green-Light to start the Pre-Migration |  | 0 days | Tue 02/04/24 08:00 | Tue 02/04/24 08:00 |  | 3
2 |  | PMCP0 | Green-light to start the Pre-Migration | All | 0 days | Tue 02/04/24 08:00 | Tue 02/04/24 08:00
3 | System Access Part 1 |  | System Access Part 1 |  | 59 days | Tue 02/04/24 08:00 | Fri 21/06/24 17:00 | 1 | 41
4 | Technical Set-up |  | Technical Set-up |  | 4 days | Tue 02/04/24 08:00 | Fri 05/04/24 17:00
11 | Parties Setup by ECMS operator |  | Setup of Parties by ECMS operator for Connectivity Testing |  | 5 days | Mon 08/04/24 08:00 | Fri 12/04/24 17:00
14 |  | ECMS.CN.OP.CSDTPAPT | Set-up CSDs and TPAs as a Party | ECMS operator | 4 days | Mon 08/04/24 08:00 | Thu 11/04/24 17:00 | 9 | 15SS
15 |  | ECMS.CN.OP.CSDTPAAAU | Set-up of the A2A users for the CSDs / TPAs | ECMS operator | 4 days | Mon 08/04/24 08:00 | Thu 11/04/24 17:00 | 14SS | 25,16
17 | NCB Connectivity Execution |  | NCB Connectivity Testing Execution |  | 10 days | Mon 15/04/24 08:00 | Fri 26/04/24 17:00
22 | CSD / TPA Connectivity Execution |  | CSD / TPA Connectivity Execution |  | 50 days | Mon 15/04/24 08:00 | Fri 21/06/24 17:00
24 | Registration Forms Verification |  | NCB, CSD, TPA registration forms data verification |  | 50 days | Mon 15/04/24 08:00 | Fri 21/06/24 17:00
25 |  | ECMS.CN.CB.RFDV1 | NCB, CSD, TPA registration form data verification (connectivity data part) | NCB user | 50 days | Mon 15/04/24 08:00 | Fri 21/06/24 17:00 | 18SS,13,15
26 | System Access Part 2 |  | System Access Part 2 |  | 40 days | Mon 29/04/24 08:00 | Fri 21/06/24 17:00 |  | 41
27 | CTPY Setup for Connectivity |  | CTPY Setup for Connectivity |  | 5 days | Mon 29/04/24 08:00 | Fri 03/05/24 17:00
28 |  | ECMS.CN.CB.CTPYPT (in PMS V1.4 ECMS.CN.CTPYPTC) | Counterparty Party Creation | NCB user | 5 days | Mon 29/04/24 08:00 | Fri 03/05/24 17:00 | 19 | 29SS,30SS,31SS
29 |  | ECMS.CN.CB.CTPYBRC | Counterparty Business Role Creation | NCB user | 5 days | Mon 29/04/24 08:00 | Fri 03/05/24 17:00 | 28SS
30 |  | ECMS.CN.CB.CTPYTAC | Technical Address Creation (Counterparty) | NCB user | 5 days | Mon 29/04/24 08:00 | Fri 03/05/24 17:00 | 28SS
31 |  | ECMS.CN.CB.CTPYAU | Set-up CPTY Administror users | NCB user | 5 days | Mon 29/04/24 08:00 | Fri 03/05/24 17:00 | 28SS | 38
37 | CTPY Connectivity Execution |  | Counterparties Connectivity Execution |  | 35 days | Mon 06/05/24 08:00 | Fri 21/06/24 17:00
38 |  | ECMS.CN.CTPY.AUSA | System Access CTPY in U2A | CPTY admin | 35 days | Mon 06/05/24 08:00 | Fri 21/06/24 17:00 | 31,35 | 39SS
39 |  | ECMS.CN.CTPY.CTPYAAU | Set-up of the A2A users for the Counterparties | CPTY admin | 35 days | Mon 06/05/24 08:00 | Fri 21/06/24 17:00 | 38SS | 40SS
40 |  | ECMS.CN.CTPY.SAA | System Access CPTY in A2A | CPTY user | 35 days | Mon 06/05/24 08:00 | Fri 21/06/24 17:00 | 39SS
41 | Mitigation Window 1 |  | Buffer to complete connectivity execution |  | 30 days | Mon 24/06/24 08:00 | Fri 02/08/24 17:00 | 3,26 | 43
42 |  | Buffer | Completion of delayed connectivity testing execution activities | All | 6 wks | Mon 24/06/24 08:00 | Fri 02/08/24 17:00
43 | PMCP1 |  | System access verification completed. ECMS connected to other systems |  | 0 days | Mon 05/08/24 08:00 | Mon 05/08/24 08:00 | 41 | 60,51
44 |  | PMCP1 | Confirmation of the connectivity testing execution | All | 0 days | Mon 05/08/24 08:00 | Mon 05/08/24 08:00 |  | 47,49
45 | Premigration preparation |  | Premigration preparation activites |  | 1 day | Mon 05/08/24 08:00 | Mon 05/08/24 17:00
46 | Snapshot of connectvity data |  | Snapshot of the connectivity data |  | 1 day | Mon 05/08/24 08:00 | Mon 05/08/24 17:00
48 | Unwanted Access Prevention |  | Prevention of unwanted access during the pre-migration |  | 1 day | Mon 05/08/24 08:00 | Mon 05/08/24 17:00
49 | <New Task> | ECMS.PM.OP.CTPYDEAC | Deactivation of CTPY users access | ECMS operator | 1 day | Mon 05/08/24 08:00 | Mon 05/08/24 17:00 | 44 | 50SS
50 | <New Task> | ECMS.PM.OP.CCQUEUE | Closing and cleaning of the ECMS inbond and outbond queues | ECMS operator | 1 day | Mon 05/08/24 08:00 | Mon 05/08/24 17:00 | 49SS
51 | Set-up of T2S for ECMS |  | T2S configuration setup for the ECMS |  | 20 days? | Mon 05/08/24 08:00 | Fri 30/08/24 17:00 | 43 | 149FS+5 days
52 | Set-up of T2S for ECMS |  | Configuration to be done in T2S by NCB and CSDs |  | 20 days | Mon 05/08/24 08:00 | Fri 30/08/24 17:00
55 | Set-up of T2S users in ECMS |  | Configuration of the T2S users in the ECMS |  | 15 days? | Mon 12/08/24 08:00 | Fri 30/08/24 17:00
60 | Reference Data Part 1 |  | Reference Data Part 1 |  | 5 days | Mon 05/08/24 08:00 | Fri 09/08/24 17:00 | 43
61 | System Parameter Configuration |  | Configuration of the parameters the responsibility of the ECMS operator |  | 5 days | Mon 05/08/24 08:00 | Fri 09/08/24 17:00 |  | 83
68 | NCB Ref Data |  | NCB Reference Data Setup |  | 5 days | Mon 05/08/24 08:00 | Fri 09/08/24 17:00 |  | 84
82 | PMCP2 |  | System parameters and NCB reference data setup completed |  | 0 days | Mon 12/08/24 08:00 | Mon 12/08/24 08:00 |  | 85,86
83 |  | PMCP2.1 | Confirmation of the system parameter set-up | NCB & ECMS operator | 0 days | Mon 12/08/24 08:00 | Mon 12/08/24 08:00 | 61
84 |  | PMCP2.2 | Confirmation of the NCB Reference data set-up | NCB user | 0 days | Mon 12/08/24 08:00 | Mon 12/08/24 08:00 | 68
85 | Reference Data Part 2a |  | Reference Data Part 2a (Ctpy data, Accounts & Pools) |  | 10 days | Mon 12/08/24 08:00 | Fri 23/08/24 17:00 | 82
86 | Accounts Setup |  | Accounts Setup |  | 5 days | Mon 12/08/24 08:00 | Fri 16/08/24 17:00 | 82 | 101117
101 | Pools Setup |  | Pools Setup |  | 5 days | Mon 19/08/24 08:00 | Fri 23/08/24 17:00 | 86 | 118
116 | PMCP3 |  | Accounts and Pool reference data capture completed |  | 0 days | Fri 23/08/24 17:00 | Fri 23/08/24 17:00 |  | 119
117 |  | PMCP3.1 | NCB confirmation that Accounts setup is completed | NCB user | 0 days | Fri 23/08/24 17:00 | Fri 23/08/24 17:00 | 86
118 |  | PMCP3.1 | NCB confirmation that Pools setup is completed | NCB user | 0 days | Fri 23/08/24 17:00 | Fri 23/08/24 17:00 | 101
119 | Reference Data Part 2b |  | Reference Data Part 2b (other ref data) |  | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00 | 116
120 | Counterparty Ref Data |  | Counterparty Ref Data |  | 5 days | Mon 26/08/24 08:00 | Fri 30/08/24 17:00 |  | 145FS+5 days
121 |  | ECMS.PM.CB.CTPY.AEC | Address Email Creation (Party/ Counterparty) | NCB user | 5 days | Mon 26/08/24 08:00 | Fri 30/08/24 17:00
122 |  | ECMS.PM.CB.CTPY.AMC | Address Mail Creation (Party/ Counterparty) | NCB user | 5 days | Mon 26/08/24 08:00 | Fri 30/08/24 17:00
123 |  | ECMS.PM.CB.CTPY.CIC | Contact Information Creation (Party/ Counterparty) | NCB user | 5 days | Mon 26/08/24 08:00 | Fri 30/08/24 17:00
124 | <New Task> | ECMS.PM.CB.CTPYCCCFG | Configuration of counterparty credit claims parameters | NCB user | 5 days | Mon 26/08/24 08:00 | Fri 30/08/24 17:00
130 | Message Subscription |  | Message Subscription Configuration |  | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00 |  | 146
132 |  | ECMS.PM.CB.CTPYMS | Message Subscription for Counterparty | NCB user | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00
133 | Set-up Users and Access Rights |  | Remaining ECMS Users Set-up |  | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00 |  | 147
134 | <New Task> | ECMS.PM.OP.CTPYREAC | Reactivation of CTPY users access | ECMS operator | 1 day | Mon 26/08/24 08:00 | Mon 26/08/24 17:00
136 |  | ECMS.PM.CTPY.CTPYU | Set-up of all CPTY Users and access right | CPTY admin | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00
137 | CTPY Registration Form Verification |  | CTPY Registration Form and other static data verification |  | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00
138 |  | ECMS.PM.CTPY.RFDV | Registration form and other static data verification (CPTY) | CPTY user | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00
139 | Common Components Set-up |  | Configuration of the ECMS billing in CRDM |  | 10 days | Mon 26/08/24 08:00 | Fri 06/09/24 17:00 |  | 148
144 | PMCP4 |  | Pre-migration activities completed |  | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 |  | 150
145 |  | PMCP4.1 | Confirmation of the CTPY Reference data set-up | NCB user | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 | 120FS+5 days
146 |  | PMCP4.2 | Confirmation of message subscription configuration | NCB user | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 | 130
147 |  | PMCP4.3 | Confirmation of users set-up | NCB user | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 | 133
148 |  | PMCP4.4 | Confirmation of Common Components set-up | NCB user | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 | 139 | 152
149 |  | PMCP4.5 | NCB confirmation that T2S setup of ECMS related data is completed | NCB user | 0 days | Fri 06/09/24 17:00 | Fri 06/09/24 17:00 | 51FS+5 days
150 | Mitigation Window 2 |  | Additional time to complete Pre-Migration Activities |  | 10 days | Mon 09/09/24 08:00 | Fri 20/09/24 17:00 | 144
151 |  | Buffer | Completion of delayed Pre-Migration activities | All | 10 days | Mon 09/09/24 08:00 | Fri 20/09/24 17:00 |  | 154
152 | Pre-migration Pre-evaluation |  | Pre-migration Pre-evaluation |  | 10 days | Mon 09/09/24 08:00 | Fri 20/09/24 17:00 | 148 | 153
153 |  | SNAPSHOT.3 | Snapshot Capture of the prod environment after pre-migration | ECMS operator | 1 day | Mon 23/09/24 08:00 | Mon 23/09/24 17:00 | 152
154 | Pre-migration Evaluation |  | Pre-migration Evaluation |  | 10 days | Mon 23/09/24 08:00 | Fri 04/10/24 17:00 | 151 | 155
155 | Go - No Go Decision |  | Go - No Go Decision |  | 0 days | Fri 04/10/24 17:00 | Fri 04/10/24 17:00 | 154