## Foglio1
Phase | Area | Start | End | Activity | CTPY action required | Internal notes
Preparation Environment | Local System | 2025-05-30 | 2025-05-30 | Cut-off banche invio "valore mandati di corrispondenza" (cfr mail del 12 maggio) | Yes | Raccolta dati aggiornati da parte delle banche e calcolo del CF aggiuntivo per garanzia assegni circolari
Preparation Environment | Reference Data | 2025-05-30 | 2025-05-30 | Cut-off modifiche dati in PROD per generazione snapshot | Yes
Eurosystem Check Point | MWCP2.0 | 2025-06-02 10:00 | 2025-06-02 10:00 | Green light to start Migration Weekend Preparation Weeks Activities
Preparation Weeks | Reference Data | 2025-06-02 10:00 | 2025-06-06 17:00 | Last update of the reference data | For information
Preparation Weeks | Local System | 2025-06-02 10:00 | 2025-06-13 12:00 | Request CTPY to demobilise MA affected by CA event to be paid after the go-live | Yes
Preparation Weeks | Local System | 2025-06-02 10:00 | 2025-06-12 12:00 | Reject collateral or credit instructions in local CMS with intended settlement date after go-live | For information | solo CCBM. Il domestico viene già scartato dal CAT
Preparation Weeks | Reference Data | 2025-06-03 12:00 | 2025-06-03 16:00 | Upload DTT Files ‐ 3.1. Credit Claims Obligors | For information
Preparation Weeks | Local System | 2025-06-04 17:00 | 2025-06-04 17:00 | Cut-off for Portafoglio Prestiti | Yes
Preparation Weeks | Local System | 2025-06-06 17:00 | 2025-06-06 17:00 | Cut-off for Prestiti singoli | Yes
Preparation Weeks | Local System | 2025-06-06 17:00 | 2025-06-06 17:00 | Chiusura ABACO | Yes
Preparation Weeks | Reference Data | 2025-06-09 08:00 | 2025-06-11 18:00 | Upload DTT Files ‐ 3.1. Credit Claims | For information
Preparation Weeks | Reference Data | 2025-06-09 08:00 | 2025-06-11 18:00 | Upload DTT Files ‐ 3.1. Credit Claims Obligors | For information
Preparation Weeks | Reference Data | 2025-06-09 08:00 | 2025-06-11 18:00 | Upload DTT Files ‐ 3.1. Credit Claims Guarantee | For information
Preparation Weeks | Reference Data | 2025-06-09 08:00 | 2025-06-11 18:00 | Upload DTT Files ‐ 3.1. Credit Claims Rating | For information
Preparation Weeks | Reference Data | 2025-06-09 08:00 | 2025-06-11 18:00 | Upload DTT Files ‐ 3.1. Add-on Haircut | For information
Preparation Weeks | Reference Data | 2025-06-11 18:00 | 2025-06-11 20:00 | Reception of Credit Claims Ref Data Report (for reconciliation) | For information
Preparation Weeks | Local System | 2025-06-12 12:00 | 2025-06-12 12:00 | Cut-off for CCBM instructions when BDI is HCB | Yes
Preparation Weeks | Reference Data | 2025-06-13 08:00 | 2025-06-13 12:00 | Provision of the ECMS CC Id to the Counterparties | Yes
Eurosystem Check Point | MWCP2.1 | 2025-06-13 12:00 | 2025-06-13 12:00 | Completion of Migration Weekend Preparation Weeks Activities
Preparation Weeks | Local System | 2025-06-13 12:00 | 2025-06-13 12:00 | Cut-off Rimborsi Marginal Lending giorni precedenti | Yes
Preparation Weeks | Local System | 2025-06-13 12:00 | 2025-06-13 16:00 | Request CTPY to close pending settlement instructions | Yes
Preparation Weeks | Local System | 2025-06-13 12:00 | 2025-06-13 16:00 | Cancel unmatched settlement instructions | For information
Preparation Weeks | Local System | 2025-06-13 15:00 | 2025-06-13 15:00 | Cut-off for Domestic MA instructions | Yes
Preparation Weeks | Local System | 2025-06-13 17:00 | 2025-06-13 18:15 | Check Marginal Lending | For information
Preparation Weeks | Local System | 2025-06-13 18:00 | 2025-06-13 20:00 | Business closure of local CMSs for 13/06 EOD | For information
Preparation Weeks | Local System | 2025-06-13 18:15 | 2025-06-13 18:40 | Disattivazione interazione tra CMS locale e T2 | For information
Preparation Weeks | Local System | 2025-06-13 18:45 | 2025-06-13 18:55 | CAT: Invio 6A6 fine giornata | Yes
Eurosystem Check Point | MWCP2.2 | 2025-06-13 20:00 | 2025-06-13 20:00 | Confirmation that the Migration Weekend activities can start
Migration Weekend | Local System | 2025-06-13 20:00 | 2025-06-15 | Dismissione messaggistica RNI CAT | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.1. Marketable Asset Position - domestic | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.1. Marketable Asset Position - as CCB | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.2. Credit Claim Positions | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.3. Externally Managed Collateral Position | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.3. Cash as Collateral | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.3. Fixed Term Deposit | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.4. Monetary Policy Operation | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.4. Early Repayment | For information
Migration Weekend | Transactional Data | 2025-06-13 20:00 | 2025-06-14 07:00 | Upload DTT Files ‐ 4.4. Credit Freezing Position | For information
Eurosystem Check Point | MWCP2.3 | 2025-06-14 07:00 | 2025-06-14 07:00 | Confirmation that all Transactional Data DTT files are uploaded
Eurosystem Check Point | MWCP2.4 | 2025-06-14 14:00 | 2025-06-14 14:00 | Confirmation of the migration of collateral and credit positions
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking MA domestic positons valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking CC positions valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking EMC valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking Cash as Collateral valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking FTD valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking OMO valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Checking Credit Freezing valuation consistency | For information
Migration Weekend | Transactional Data | 2025-06-14 18:05 | 2025-06-14 20:05 | Check Suggested CL consistency | For information
Eurosystem Check Point | MWCP2.5 | 2025-06-14 21:05 | 2025-06-14 21:05 | Confirmation of the pool valuation processes
Migration Weekend | Corporate Actions | 2025-06-14 21:05 | 2025-06-14 21:05 | Inform CSDs they can start sending CANO/NEWM to the ECMS | For information
Migration Weekend | Corporate Actions | 2025-06-14 21:05 | 2025-06-15 06:35 | Reception and Processing of CANO/NEWM messages from CSDs | For information
Migration Weekend | Transactional Data | 2025-06-14 22:50 | 2025-06-14 23:50 | Check Credit Lines and Payments in CLM | For information
Eurosystem Check Point | MWCP2.6 | 2025-06-14 23:50 | 2025-06-14 23:50 | Confirmation of the CL update in CLM
Eurosystem Check Point | MWCP2.7 | 2025-06-15 06:30 | 2025-06-15 06:30 | Greenlight to open the system to the counterparties
Migration Weekend | Couterparty | 2025-06-15 07:00 | 2025-06-15 07:00 | Reactivation of Counterparties' Users and inform they can access to the ECMS | Yes
Migration Weekend | Couterparty | 2025-06-15 07:00 | 2025-06-15 10:00 | Inform Euroclear and pre-identified Counterparties they can start penny test | Yes
Migration Weekend | T2/T2S | 2025-06-15 11:00 | 2025-06-15 21:00 | Start of maintenance window | For information
Migration Weekend | Counterparty | 2025-06-15 07:00 | 2025-06-15 14:00 | Counterparties checks of migrated data | Yes
Migration Weekend | Counterparty | 2025-06-15 07:00 | 2025-06-15 14:00 | Chance for setting MaCL for Counterparties willing to set it | Yes
Eurosystem Check Point | MWCP2.8 | 2025-06-15 13:00 | 2025-06-15 13:00 | End of Migration Weekend Activities
Migration Weekend |  | 2025-06-15 14:00 | 2025-06-15 14:00 | End of Migration and NSD support - Operations will resume on 16th at 7:00 AM | For information